## Sheet1
Quality Management Plan (P1)
Section | Details
Project Title
Project Manager / QC Manager
Date
Project Scope (QC Focus) | Outline the deliverables/processes that require quality control.
Quality Objectives | Define measurable quality goals (e.g., “concrete strength ≥ M30,” “defect rate ≤ 2%”).
Applicable Standards / Codes | IS Codes, NBC, ISO, PMI, Client Specifications, etc.
QC Team & Responsibilities | List of QC engineer, site supervisor, external consultants, labs.
Part 2 ( QC Activities & Inspection Plan)
WBS Code | Activity / Deliverable | QC Standard / Criteria | Inspection & Test Method | Frequency | Responsible Person | Acceptance Criteria | Records / Reports
1.1 | Material Procurement | IS Codes / Approved Vendor List | Lab testing, vendor certificate | Each batch | QC Engineer | Meets IS code requirements | Material Test Report
1.2 | Concrete Works | IS 456, Mix Design | Cube test, slump test | Daily / per pour | Site Engineer | Compressive strength ≥ design | Cube Test Report
1.3 | Steel Reinforcement | IS 1786, Approved Drawing | Physical check, lab test | Each delivery & before casting | QC Engineer | Yield strength ≥ 500 N/mm² | Steel Test Report
1.4 | Masonry | IS 1905, drawings | Visual inspection, level & plumb check | Continuous | Site Supervisor | Alignment, mortar ratio as per spec | Site QC Log
1.5 | Waterproofing | Manufacturer specs, IS codes | Flood test, visual inspection | Each application | QC Engineer | No leakage within 72 hrs | QC Checklist
1.6 | Electrical Works | IS standards / consultant drawings | Continuity, insulation resistance test | Each circuit | MEP QC Engineer | As per safety standards | Test Certificates
1.7 | Final Finishes | Client-approved samples | Mock-up approval, visual inspection | Per unit | Site Engineer + Client | Defect-free, uniform finish | Snag List, Sign-off
Part 3 Non-Conformance & Corrective Action Plan
NC No. | Activity | Non-Conformance Observed | Root Cause | Corrective Action | Responsible | Target Date | Closure Verified By
001 | Concrete Works | Compresstion test 20MPA | Wrong Mix desgin | Change the Mix Design & Structural Member strengthing | RMC Plant operator | Before next concreting | RCC Consultant
Annexures : Quality Records & Documentation
Test reports (cube test, steel test, MEP certificates)
Site QC checklists
Inspection reports
Snag lists and closure reports
Handover quality certificates