## Sheet1
Part 1Project Monitoring Report Template
Section | Details
Project Title
Project Manager
Report Date
Reporting Period | (From – To)
Prepared For | (Sponsor / Steering Committee / Client)
Part 2 ( Detailed Montiering report)
1. Integration Management
Status of project charter, management plan, change requests.
Summary of approved/rejected changes.
Overall project health (RAG: Red / Amber / Green).
2. Scope Management
Planned Deliverables | Achieved Deliverables | Variance | Remarks
3. Schedule Management
Milestone | Baseline Date | Actual / Forecast Date | Variance (Days) | Status
4. Cost Management
Budgeted Cost (BAC) | Actual Cost (AC) | Earned Value (EV) | Cost Variance (CV) | Cost Performance Index (CPI)
5. Quality Management
Key inspections/tests performed.
Non-conformities raised & closed.
Pending QC issues.
6. Resource Management
Resource Type | Planned | Deployed | Variance | Remarks
Labour
Equipment
Consultants
7. Communication Management
Key meetings held (dates, agenda, outcomes).
Reports/updates shared with stakeholders.
Issues in stakeholder communication.
8. Risk Management
Risk ID | Description | Probability | Impact | Status | Mitigation / Action
9. Procurement Management
Package | Vendor | Planned Award Date | Actual / Forecast | Remarks
10. Stakeholder Management
Engagement activities carried out.
Issues/concerns raised by stakeholders.
Corrective actions taken.
Part 3 ( Earned Value Management)
Metric | Formula | Value | Interpretation
Planned Value (PV) | Budgeted cost of work scheduled
Earned Value (EV) | Budgeted cost of work performed
Actual Cost (AC) | Actual cost of work performed
Cost Variance (CV) | EV – AC |  | CV > 0 = Under budget, CV < 0 = Over budget
Schedule Variance (SV) | EV – PV |  | SV > 0 = Ahead of schedule, SV < 0 = Behind schedule
Cost Performance Index (CPI) | EV ÷ AC |  | CPI > 1 = Cost efficient, CPI < 1 = Overrun risk
Schedule Performance Index (SPI) | EV ÷ PV |  | SPI > 1 = Ahead of schedule, SPI < 1 = Delay risk
Estimate at Completion (EAC) | BAC ÷ CPI (common formula) |  | Predicted final cost
Estimate to Complete (ETC) | EAC – AC |  | Remaining expected cost
Variance at Completion (VAC) | BAC – EAC |  | Expected cost variance
Part 4 ( summary ) Red Amber Green Status
Knowledge Area | Status (R/A/G) | Key Issues | Action Plan
Integration
Scope
Schedule
Cost
Quality
Resources
Communication
Risk
Procurement
Stakeholder