## Sheet1
Risk ID | Risk Description | Category | Probability (0–1) | Impact (1–5) | Risk Score (P × I) | Qualitative Priority (Low/Med/High) | Cost Impact (₹) | EMV (₹) CI x Probablity | Schedule Impact (Days) | Response Strategy (Avoid/Mitigate/Transfer/Accept) | Risk Owner | Triggers / Early Warning Signs | Status (Open/Monitoring/Closed) | Notes
R1 | Delay in steel delivery | Schedule | 0.6 | 4 | 2.4 | High | 5,00,000 | 3,00,000 | 21 | Mitigate | Procurement Manager | Supplier late on first shipment | Monitoring | Buffer stock planned
R2 | Unexpected monsoon rains | Environmental | 0.3 | 5 | 1.5 | Medium | 2,00,000 | 60000 | 10 | Accept | Site Manager | Weather forecast warnings | Open | May shift some activities indoors
R3 | Skilled labour shortage | Resource | 0.4 | 3 | 1.2 | Medium | 3,50,000 | 1,40,000 | 15 | Transfer | HR Lead | Recruitment delays | Monitoring | Using manpower agency backup
R4 | New government tax policy | Regulatory | 0.2 | 5 | 1 | Low | 8,00,000 | 1,60,000 | 0 | Accept | Finance Lead | Policy draft announcement | Open | Watch news for updates
R5 | Supplier offers early delivery discount | Opportunity | 0.5 | 4 | 2 | High | -1,00,000* | -50000 | -7 | Exploit | Procurement Manager | Supplier email offer | Open | Adjust schedule to receive early