## Sheet1
Part 1 Stakeholder Engagement Plan Template
Section | Details
Project Title
Prepared By
Date
Project Objective (for stakeholder engagement) | Outline how engagement will support project success.
Engagement Goals | Examples: ensure smooth approvals, build trust, manage expectations, reduce risks.
Approach / Strategy | e.g., Transparent communication, regular updates, active consultation, conflict resolution.
Tools & Methods | Meetings, workshops, newsletters, reports, dashboards, public hearings, digital platforms.
Monitoring & Review | How engagement effectiveness will be tracked (surveys, feedback forms, meeting minutes, KPIs).
Part 2 Stakeholder analysis Matrix
Stakeholder | Category (Internal/External, Gov’t, Client, Contractor, Community, etc.) | Interest in Project | Influence / Power | Impact of Project on Them | Engagement Strategy | Communication Method & Frequency | Responsible Person
Project Sponsor | Internal – Investor/Owner | High – wants ROI & timely delivery | High | Benefits directly from success | Manage closely | Weekly reports, monthly review meetings | Project Manager
Local Authority (BMC / SRA) | Government | Moderate – focus on compliance | High | Project dependent on their approvals | Keep satisfied | Regular submission, monthly liaison | Liaison Officer
Society Residents | Beneficiaries / End Users | High – housing & lifestyle impact | Medium | Directly affected by redevelopment | Consult & involve | Weekly society meetings, newsletters | Community Manager
Contractors | Execution Partner | High – delivery & payment interest | Medium | Dependent on project for revenue | Collaborate | Weekly site meetings, progress dashboards | Site PM
Financial Institution | External – Bank / NBFC | High – repayment & risk | High | Exposure to financial risk | Manage closely | Monthly progress & cash flow updates | Finance Head
Local Community / NGOs | External – Neighborhood Stakeholders | Medium – concerned about disruption | Low | Affected by construction activities | Keep informed | Quarterly meetings, grievance redressal | CSR Officer
Internal Project Team | Internal | High – career & workload | Medium | Responsible for delivery | Motivate & involve | Daily stand-ups, weekly reports | Project Manager
Media / Press | External | Medium – information seekers | Medium | Can shape public perception | Monitor & inform selectively | Press releases, media briefings (as needed) | PR Officer
Part 3 ( Stakeholder Engagement Levels (for mapping))
Level | Description | Example Action
Inform | Provide timely, accurate information | Newsletters, reports
Consult | Seek stakeholder feedback/input | Surveys, focus groups
Involve | Directly include in decision-making | Workshops, steering committee
Collaborate | Partner in planning & execution | Joint task forces
Empower | Give authority to decide on outcomes | Society vote on design changes
Part 4 ( Stakeholder Mapping Grid (Power vs. Interest)
High Power / High Interest | High Power / Low Interest
Manage closely (e.g., Sponsor, Bank, Authorities) | Keep satisfied (e.g., Key Govt officials, Regulatory boards)
Low Power / High Interest | Low Power / Low Interest
Keep informed (e.g., Residents, NGOs, Local community) | Monitor (e.g., Media, peripheral stakeholders)