## Sheet1
WBS / Activity | Budgeted Cost | Actual Cost | Variance (A−B) | Reason
1. Project Initiation & Planning | 600000 | 620000 | 20000 | Extra steering-committee workshops and planning iterations.
2. Requirements Elicitation & Analysis | 1200000 | 1350000 | 150000 | Additional compliance requirements expanded scope.
3. UX/UI Design | 800000 | 760000 | -40000 | Reuse of design system reduced effort.
4. Architecture & Technical Design | 750000 | 800000 | 50000 | Extra performance benchmarking spikes.
5.1 Front-end Development | 1800000 | 1900000 | 100000 | Accessibility rework and cross-browser fixes.
5.2 Back-end / Microservices | 2600000 | 2850000 | 250000 | Unexpected refactoring for legacy integration and scalability.
5.3 API Gateway & Integrations | 1000000 | 950000 | -50000 | Third-party sandbox stabilized early; fewer change requests.
5.4 Mobile App | 1200000 | 1150000 | -50000 | Code sharing with web reduced effort.
6.1 Test Planning & Cases | 400000 | 420000 | 20000 | Security-driven additional test scenarios.
6.2 Unit & Integration Testing | 600000 | 650000 | 50000 | Flaky tests stabilization and tooling time.
6.3 System & Regression Testing | 700000 | 780000 | 80000 | Extended regression window to fix a P1 defect.
6.4 UAT Support | 500000 | 600000 | 100000 | Client requested an additional UAT cycle.
7.1 CI/CD Setup | 550000 | 500000 | -50000 | Leveraged existing org pipelines and templates.
7.2 Cloud Infra (IaaS/PaaS) | 900000 | 1100000 | 200000 | Higher load-test usage; reserved instances not activated in time.
7.3 Monitoring & Observability | 350000 | 300000 | -50000 | Consolidated tools (logs, APM) lowered licenses.
8. Security & Compliance | 600000 | 700000 | 100000 | Premium external penetration test and remediation sprint.
9.1 Data Modeling & ETL | 700000 | 650000 | -50000 | Simplified transformations after early data profiling.
9.2 Reports & Dashboards | 500000 | 520000 | 20000 | Added executive KPI pack and drill-downs.
10. Documentation & Knowledge Transfer | 300000 | 280000 | -20000 | Auto-generated API docs and templates.
11. Training & Change Management | 350000 | 400000 | 50000 | Extra training cohorts for operations and support.
12. Hypercare (30 days) | 450000 | 520000 | 70000 | Extended on-call coverage to stabilize go-live.
13. Project/Program Management | 800000 | 780000 | -20000 | Lower T&E and overheads in later sprints.
14. Contingency (Management Reserve) | 500000 | 300000 | -200000 | Partial utilization of management reserve only.
TOTAL | 18150000 | 18880000 | 730000 | Overall program variance due to cloud usage spike, UAT extension, and security hardening.