## Sheet1
WBS Code | Level | Task/Deliverable | Description
1 | Project | Redevelopment Project | End-to-end delivery of redevelopment
1.1 | Phase 1 | Initiation & Approvals | Activities required to initiate the project
1.1.1 | Work Package | Feasibility Study | Market, legal, and financial feasibility
1.1.2 | Work Package | Consent & Agreements | Obtaining 70% tenant consent, drafting agreements
1.1.3 | Work Package | Regulatory Approvals | SRA/MHADA/BMC approvals
1.2 | Phase 2 | Design & Planning | Preparation of designs and execution plan
1.2.1 | Work Package | Architectural Design | Concept, schematic, and detailed drawings
1.2.2 | Work Package | Structural Design | Structural analysis and design
1.2.3 | Work Package | MEP Design | Mechanical, electrical, plumbing designs
1.3 | Phase 3 | Construction | Actual redevelopment work
1.3.1 | Work Package | Site Preparation | Demolition, clearing, leveling
1.3.2 | Work Package | Foundation | Excavation, piling, foundation works
1.3.3 | Work Package | Superstructure | RCC framework, walls, slabs
1.3.4 | Work Package | Finishes & Services | Plastering, flooring, painting, MEP works
1.4 | Phase 4 | Handover & Closing | Delivery of project to stakeholders
1.4.1 | Work Package | Occupation Certificate | Liaison with authorities
1.4.2 | Work Package | Handover Units | Allotment of flats to society members
1.4.3 | Work Package | Final Closure Report | Documentation, lessons learned, financial closure